## Slide 1: PM Role in an AI World: the session at a glance
PM SUMMIT 2026 · THURSDAY 5 NOVEMBER · EVERY REGION
120 minutes, the same in every region. One outcome: an agent every room tries the week after.
10 min
2 × 15 min
60 min · breakout rooms
20 min
0′
10′
40′
100′
120 min
1
Introduction
10 min · plenary · moderator
Why the PM role is changing
Goal: define your work around AI
Everyone already knows their room
2
AI use cases
2 × 15 min · plenary · 2 speakers
Two real AI use cases
What it took and what it gave back
Sets the bar for the pilots
3
Breakout · Pain to Pilot
60 min · rooms C1–C6 · group lead + team
Orient 5′
Map the hours 10′
Design 12′
Build & challenge 15′
Fix & decide 8′
Commit 10′
One case, one agent, one pilot per room
Agent takes routine, PM keeps judgment
Output: Pilot Pack + 90-second summary
4
Wrap-up
20 min · plenary · debrief host
Summit Debrief: 90 s per room
What each room tries next week
Feedback coordinators named
BEFORE · BY TUE 3 NOV
Rooms allocated in the invitation (29 Oct)
Pre-work: story, case file, own week
Group lead per room with Agent Builder
SITE OWNERS · ON THE DAY
A space per room near the plenary
Laptop, screen, network, tool access
Case, sample data and Pilot Pack
AFTER THE SUMMIT
Each room tries its agent the next week
Feedback coordinators collect results
30-day readout in early December
Notes: Walk through the session left to right. 1. Introduction (10 min, plenary): why the PM role is changing, and the goal of the session: define your work around AI. Participants already know their room, so they go straight in afterwards. 2. AI use cases (2 x 15 min, plenary): two real use cases show what an agent can take over and what it took to get there. 3. Breakout (60 min, rooms C1 to C6): each room works one KESTREL case. The group lead runs the room and builds the agent in Agent Builder; the team checks and records the results. Every room leaves with a Pilot Pack and a 90-second summary. 4. Wrap-up (20 min, plenary): the Summit Debrief. Each room shares its 90-second summary: what it will try next week, the time it could save and what it still has to fix. Feedback coordinators are named. Before: rooms are allocated in the invitation on 29 Oct and pre-work is done by 3 Nov; every group lead has Agent Builder activated. On the day, site owners provide a space per room near the plenary, a laptop, screen, network and tool access, and the case, sample data and Pilot Pack. After: every room tries its agent the week after the summit, the feedback coordinators collect the results, and the 30-day readout follows in early December.

## Slide 2: How the breakout unfolds
BREAKOUT · 60 MINUTES · COMMON PLAN FOR ALL ROOMS
Six steps per room. Every Pilot Pack records results, unfinished work and next steps.
MINUTES
STEP
WHAT THE ROOM DOES
CHECKPOINT · WHAT MUST EXIST
00–05′
1
Orient
The group lead reads the case aloud, assigns roles and opens Agent Builder.
Roles assigned. Agent Builder ready to use
05–15′
2
Map the hours
Estimate time per task. Pick repetitive work the agent can help with and a use for the time saved.
Current hours per PM per week and expected benefit
15–27′
3
Design the agent
Write instructions and what the PM still decides. Define a key failure and what counts as passing each test.
Three tests: quality, time saved, PM approval rules
27–42′
4
Build & challenge
The group lead builds the agent and runs three tests. Other members check results and suggest modifications.
Results and task time, including PM review, recorded
42–50′
5
Fix & decide
Fix and rerun failed tests. Agree what the agent must check with the PM before acting.
Instructions updated. Tests passed or fixes still needed.
50–60′
6
Package & commit
Choose a feedback coordinator and a task for everyone next week, once tests pass and access is ready.
Coordinator on card. Pack submitted. 90‑second summary practised.
AFTER
Summit Debrief
opens the wrap-up
Return for the proposed wrap-up. Each room shares a 90‑second summary.
What you’ll try next week, time you could save and what to fix
WHO IS IN EVERY ROOM
Max. 8 people, mixed experience
Group lead: facilitates and builds
Team: checks and records results
WHAT EVERY ROOM NEEDS
A space near the whole-group session
Laptop, screen, network and tool access
Case, sample data and Pilot Pack
IF SOMETHING GOES WRONG
Running late? Keep checks and next steps.
Group lead absent? Choose a replacement.
Notes: The 60-minute breakout: one common plan for all rooms. Before the day: every participant knows their room and case (C1 to C6) from the invitation and has done the pre-work. Each group lead has Agent Builder activated in Copilot Premium. 1. Orient, 0 to 5: the group lead reads the case aloud, assigns roles and opens Agent Builder. Checkpoint: roles assigned, Agent Builder ready to use. 2. Map the hours, 5 to 15: estimate the time per task, pick the repetitive work the agent can help with and a use for the time saved. Checkpoint: current hours per PM per week and the expected benefit. 3. Design the agent, 15 to 27: write the instructions and what the PM still decides; define a key failure and what counts as passing each test. Checkpoint: three tests: quality, time saved, PM approval rules. 4. Build & challenge, 27 to 42: the group lead builds the agent and runs the three tests; the other members check the results and suggest modifications. Checkpoint: results and task time, including the PM review, recorded. 5. Fix & decide, 42 to 50: fix and rerun failed tests; agree what the agent must check with the PM before acting. Checkpoint: instructions updated; tests passed, or the fixes still needed. 6. Package & commit, 50 to 60: choose a feedback coordinator and a task for everyone next week, once tests pass and access is ready. Checkpoint: coordinator on the card, Pilot Pack submitted, 90-second summary practised. After: the rooms return for the wrap-up, where each room shares its 90-second summary: what it will try next week, the time it could save and what it still has to fix. Every room: at most 8 people with mixed experience. The group lead facilitates and builds; the team checks and records results. Each room needs a space near the whole-group session, a laptop, screen, network and tool access, and the case, sample data and Pilot Pack. If something goes wrong: running late, keep the checks and next steps. Group lead absent, the room chooses a replacement.

## Slide 3: Frequently asked questions
FAQ · FOR REGIONAL MODERATORS AND SITE OWNERS
Left: before the summit. Right: on the day and after.
1
How are people assigned to rooms?
Upfront, by the regional lead, final on 26 Oct. The invitation (29 Oct) names each person’s room and case file, C1–C6.
2
What must participants do before 5 November?
Read the story and their case file, map their own week, bring one idea. Done by Tue 3 Nov; nothing to prepare on the day.
3
Do participants need AI experience?
No. The group lead builds the agent with Agent Builder in Copilot Premium. The team checks results and brings experience.
4
What if a group lead doesn’t have Agent Builder yet?
Request it at forms.cloud.microsoft/e/KjfvXMztWp and confirm access by 3 Nov. It must be ready to use when the room starts.
5
Who runs each room?
A group lead named by the regional lead, who facilitates and builds the agent (briefing 23 Oct). The team checks and records results.
6
Which cases does my region run?
Every region runs C3 and C6, then adds C1, C4, C2, C5 in that order. Regions with six or more rooms run all six.
7
How many people per room?
At most 8, with mixed experience. Larger groups split into two rooms on the same case.
8
What does the site provide?
Per room: a space near the plenary, a laptop, screen, network and tool access, and the case, sample data and Pilot Pack.
9
Which data do rooms use?
Only the KESTREL case files, which hold no real project data. No customer or confidential data goes into any AI tool.
10
What if a room runs late, or the group lead is absent?
Running late: keep the checks and next steps, cut the rest. Group lead absent: the room chooses a replacement.
11
What does each room deliver?
A Pilot Pack with results, unfinished work and next steps, and a 90‑second summary for the Summit Debrief.
12
What happens after the summit?
Everyone tries the agent the next week, once tests pass and access is ready. The feedback coordinator collects the results.
Notes: The twelve questions we expect most. Left column: before the summit. Right column: on the day and after. Dates: group lead briefing Fri 23 Oct; allocation final Mon 26 Oct; invitation and pre-work sent Thu 29 Oct; pre-work done and group leads confirm Agent Builder access Tue 3 Nov; summit Thu 5 Nov; 30-day readout early December. Agent Builder access: group leads request it through the form https://forms.cloud.microsoft/e/KjfvXMztWp and confirm they can create a test agent before 3 Nov, never in the room. Data: rooms paste only the KESTREL case files into the tool. Real project data enters a pilot only through an approved tool and with data approval. Pilot Packs are submitted through the capture link, an MS Form that mirrors the Pilot Pack.