PM SUMMIT 2026 · WORKSTREAM 2 · CORE TEAM

Core-team mock run

Breakout simulation with the Pain to Pilot kit · 75 minutes, plus 30 minutes of defect triage · proposed for Fri 9 Oct · draft v0.1

| Topic | WS2 breakout simulation: turn PM pain points into pilot-ready AI opportunities with the Pain to Pilot kit. |
| --- | --- |
| Goal | Test whether the instructions, timing, Pilot Pack, roles and report-out produce a comparable, useful result without expert rescue. |
| Outcome | Two completed Pilot Packs; a defect log with severity and owner; a revised facilitator script; timing confirmed or changed; decisions on pre-work, card curation and given-versus-chosen cards; acceptance criteria for scaling to all regions. |

## Set-up: two rooms that test different things

|  | Room A | Room B |
| --- | --- | --- |
| Card | C1 Status Report Treadmill, given | Choice between C2 and a deliberately broad draft swap card: “Use AI to improve project communication” |
| Tests | The kit as designed, the 60-minute timing, the Build and challenge split | The Select variant, the swap-card standard, the paper fallback |
| Facilitator | Experienced | First-time, briefed only with the kit |
| Size | 7–8 participants (normal room) | 4–5 participants (small room) |
| AI tool | Approved tool available [tool to be confirmed] | Tool “fails” at minute 27, forcing the paper test |
| Observers | One or two | One |

An oversized room (about 12) cannot be tested with the core team alone. Test it at the facilitator dry run by merging two briefing groups. (Assumption)

## Roles

| Role | Who | Job |
| --- | --- | --- |
| Session owner | Venu Tangirala | Opens and closes, owns decisions after the debrief |
| Test facilitator, Room A | [experienced facilitator] | Runs Room A from the facilitator guide |
| Test facilitator, Room B | [first-time facilitator] | Runs Room B with the kit only; not told about injections |
| Scribes | One participant per room | Fill the Pilot Pack and give the report-out |
| Participants | Core-team members | Play themselves or a persona card (below) |
| Observers | [names] | Score with the scorecard, log defects, never rescue the room |
| Producer and timekeeper | [name] | Tests links, fires the injections on time, keeps the master clock |

Names in brackets to be assigned at the next core-team call.

## Preparation (T–3 days to the start)

- Book two breakout rooms (Teams or physical) and a main room; the producer tests every link.

- Share: C1 and C2 cards with data, the broad swap card, two blank Pilot Packs, the facilitator guide, the room slides.

- Send persona cards privately to the players. Facilitators are not told which personas exist or when injections come.

- Confirm the Room A Builder can log in to the approved tool. The tool decision is still open.

- Brief observers for 10 minutes on the scorecard workbook (WS2_Mock_Run_Scorecard.xlsx): one sheet per room, timing log, defect log.

- Open the kit’s room timer on the shared screen in each room.

## Agenda: 75 minutes

| Time | Block | What happens |
| --- | --- | --- |
| 00–05 | Briefing | Purpose of the mock run, “observers never rescue”, split into rooms. |
| 05–65 | Breakout run | Both rooms run the full 60 minutes from the kit. The producer fires the injections. |
| 65–68 | Report-outs | Room A: 90 seconds. Room B: cut to 45 seconds without warning (injection). |
| 68–75 | Hot debrief | One minute per voice: facilitators, then participants, then observers. Each observer names one top defect. |
| + 2 days | Defect triage (30 min) | Observers and WS2 go through the defect log: severity, root cause, change, owner, retest. |

## Injected failures

Times are minutes into the breakout. Together the two rooms cover all ten mock-run scenarios in the knowledge base.

| Room | Min | Injection (scenario) | The observer watches for |
| --- | --- | --- | --- |
| A | 0–60 | The Expert dominates from the start (2) | Facilitator redirects within 3 minutes: Builder role, narration, a round |
| A | 10 | Nobody can quantify the baseline (3) | An estimate range is written and marked “to be measured” |
| A | 20 | A public or unapproved tool is proposed (4) | Parked; tool approval recorded as a pilot prerequisite |
| A | 30 | “Let’s paste my real project status” (5) | Sample data kept; data approval noted in Pilot Pack section 8 |
| A | 52 | Nobody will own the pilot (8) | Owner role, who confirms the name, and by when |
| B | 0 | Two cards to choose from, one too broad (1, 6) | Choice made by minute 7; the broad card narrowed or rejected |
| B | 27 | Producer tells the Builder the tool is unavailable (tool failure) | Switch to the paper test within 3 minutes |
| B | 35 | Scribe closes the template or loses the link (7) | Offline or paper copy used; nothing lost |
| B | 40 | Facilitator called away for 5 minutes (10) | Scribe runs the room from the kit; timer keeps pace |
| B | 65 | Report-out cut to 45 seconds (9) | Three lines delivered: pain, agent and PM decision, next step |

## Persona cards (hand out privately)

| Persona | Room | How to play it |
| --- | --- | --- |
| The Expert | A | You know AI tools well. Push your own solution early, talk fast, reach for the tool before the problem is clear. |
| The Newcomer | A, B | You have never used an AI assistant at work. Ask what terms mean. Stay quiet unless invited. |
| The Real-Data PM | A | At about minute 30: “Let’s just paste my real project status, it’s more realistic.” |
| The Tool Enthusiast | A | At about minute 20, propose a public AI tool you like. |
| The Skeptic | A | Ask “who will actually use this?” At minute 50, refuse to own the pilot. |
| The Broad Thinker | B | Keep widening the scope: “it should also do reporting, risks and minutes”. |

Everyone else plays themselves. Personas make the mixed AI maturity of real rooms visible in a team that knows the design well.

## Observer scorecard

Score each item 1–5 and note evidence with the minute. 1 = did not happen or needed rescue; 3 = happened late or partly; 5 = happened on time without prompting. The workbook has one sheet per room.

| # | Item (timings follow the kit’s flow) |
| --- | --- |
| 1 | Instructions understood without clarification |
| 2 | Card chosen (Room B) by minute 7, slice chosen (both rooms) by minute 15 |
| 3 | Problem, user and baseline specific by minute 15 |
| 4 | Human decision point explicit |
| 5 | AI flow understandable to a non-expert |
| 6 | Value metric observable |
| 7 | Data and governance risk considered |
| 8 | Owner and first test present |
| 9 | All voices included |
| 10 | Report-out completed within the limit |
| 11 | Time test run and hours back per PM per week recorded (kit-specific) |
| 12 | Room recovered from each injected failure without observer help (kit-specific) |

## Pass criteria for scaling

From the knowledge base, recommended and still to be confirmed by WS2:

- 100% of the ten mandatory Pilot Pack fields completed.

- Owner, first test, metric and guardrail explicit.

- The facilitator did not need content expertise to finish.

- Someone outside the room can read both packs in three minutes and restate each one.

- No unresolved confidentiality or tool-approval issue is hidden.

- The final recommendation is produced inside the 60-minute slot.

Proposed additions: average observer score of at least 3.5 per room, and no item scored 1.

Retest trigger: any S1 defect or any missed pass criterion. Retest the changed part at the facilitator dry run.

## Defect severity

| S1 | Blocks the outcome: no pack, a mandatory field missing, a hidden confidentiality or tool issue, the room cannot finish. |
| --- | --- |
| S2 | Degrades quality or timing: a stage overruns by more than 3 minutes, a voice is excluded, a trap goes unnoticed. |
| S3 | Cosmetic or wording: unclear phrasing on a card, slide or form. |

## Debrief questions

- Facilitators: where did you feel you needed expertise you did not have?

- Where did time go? Which stage overran, and by how much?

- Given card (Room A) or a choice (Room B): which worked better? Keep a Select step?

- Which instruction, card text or form field caused confusion?

- Were the traps caught, and by what: the tool, a test, or a person?

- Could someone outside the rooms compare the two Pilot Packs?

- What would a first-time facilitator in another region need that the kit lacks?

- Which injected failure was hardest to recover from, and what would have helped?

## Decisions to close after the mock run

| Decision | Options | Needed by |
| --- | --- | --- |
| Timing per stage | Keep the 60-minute flow, or change stage lengths | Kit freeze, 16 Oct |
| Given card or a choice | Given card, or a choice of 2–3 cards with a Select step | Kit freeze |
| Room roles | Keep the Builder and Challenger split, or simplify | Kit freeze |
| Mandatory fields | Keep the ten, or trim | Kit freeze |
| Report-out | 90 seconds; 45-second fallback; how many rooms report | Kit freeze |
| Offline fallback | Paper and photo, confirmed with site owners | Kit freeze |
| Card set and swap standard | Keep all six cards; accept the swap-card template | Kit freeze |
| Pre-work | Content and send date (proposed Thu 29 Oct) | Briefing, 23 Oct |
| Scaling acceptance criteria | Confirm the pass criteria above | Kit freeze |

Dates follow the kit’s proposed timeline and are not yet agreed.

## After the mock run

- Update the kit to v1 within a week of the mock run and log what changed.

- Retest every changed part at the facilitator dry run.

- Hand the frozen package (cards, Pilot Pack, facilitator guide, slides, fallback) to the agenda and playbook team and the site owners.